## Sheet1
Feature | Design | Backend | Frontend | QA | Estemaited Date | Responsible Member | notes
AI Daily Summary | Done | Fix bug | Done | Waiting Pending Step |  | Gaith
Requests and Approvals
Ameen | Done | Enhancement | Waiting Pending Step | Waiting Pending Step |  | Gaith | نضيف الوصف والعنوان باللغتين و كمان الاولوية
Moa'amlat | Done | Fix bug | Waiting Pending Step | Waiting Pending Step |  | Aiman | نحتاج سجل الاحالات والاكشن والجهات الخارجية
Saedni | Done | Done | Fix bug | Waiting Pending Step |  | Madawi | اليبل والفاليو يطلعون ب صفوف متفرقة
Tamkeen | Done | Done | Done | Done
Signit | Done | Fix bug | Done | Waiting Pending Step |  | Gaith | يرجع للهوم بيج عند طلب التوقيع مو الملف الاصلي + وقت اختفاء المعاملة ياخذ ايام
ERP | Done | New Requerments | New Requerments | Done |  | Ibtisam | متبقى ارسال كامل تفاصيل الطلب و اكشن طلب معلومات اضافية
majlistech | Not Started | Not Started | Not Started | Not Started |  | Salman
My Sechdule
View details | Done | Done | Enhancement | Done |  | Madawi
Create new meeting | Done | Fix bug | Done | Waiting Pending Step |  | Gaith | انشاذ اونلاين ميتنق يضرب في البرودكشن
Actions (Join, Reschdule) | Done | Done | Fix bug | Waiting Pending Step |  | Madawi | متبقي ان اعادة الجدولة تكون فقط من جهة منشئ الاجتماع في البرود الجوين ابد ماطلعت ، تحسين مستقبلي باضافة خاصية Approve, Reject,,propse new time
MOM
MOM View List | Done | Fix bug | Done | Waiting Pending Step |  | Madawi | dependes on fixing connection between ws and mom
MOM details page | Done | Fix bug | In-progress | Waiting Pending Step |  |  | dependes on fixing connection between ws and mom
MOM Tasks home | Done | Fix bug | In-progress | Waiting Pending Step |  | Madawi | dependes on fixing connection between ws and mom
Create Manual MOM | Done | Fix bug | Waiting Pending Step | Waiting Pending Step |  | Madawi | dependes on fixing connection between ws and mom
uplod MOM | Done | Fix bug | In-progress | Waiting Pending Step |  | Madawi | يحتاج انه تكون كاملة الخدمة من جهة فريق mom بحيث احنا نكرر فقط الوجيك للخدمة عندنا
live recorded | Done | N/A | In-progress | Waiting Pending Step |  | Madawi
export MOM | Done | N/A | In-progress | Waiting Pending Step |  | Madawi
Teams Chats
View List of Chats | Done | N/A | Not Started | Not Started |  | Madawi
Open conversation page | Done | N/A | Not Started | Not Started |  | Madawi
Reply | Done | N/A | New Requerments | Waiting Pending Step |  | Madawi
Create new chat | Done | N/A | Not Started | Not Started |  | Madawi
Temas Call
View Missed Calls | Done | Cancelled | Cancelled | Cancelled |  | Madawi
Join Call (meeting) | Done | Done | Done | In-progress |  | Luma | تتاكد اذا يودي الريدايركشن لشاشة الاتصال
Start new Call | Done | New Requerments | New Requerments | New Requerments |  | Madawi
My Team
View live status | Done | Not Started | Not Started | Not Started |  | Salman
List of members | Done | Done | Not Started | Not Started |  | Madawi
Update Status | Done | Not Started | Not Started | Not Started |  | Salman
Recent Activity | Done | Not Started | Not Started | Not Started |  | Salman
Shared Files
Upload new files | Done | Done | Done | Done
Share file with others | Done | Done | Done | Done
View shared file | Done | Done | Done | Done
Live Collaboration | Done | Done | Done | Done
File Actions ( Reshare, Delete) | Done | Done | Done | Done
My Projects
View Project Info (name, members, prg, Deliverables) | Done | Done | Done | Done
View Project Summary | Done | Done | Done | Done
Rederication to details page | Done | Done | Done | Done
My To-Do (homepage)
View all task user have from any workspaces | Not Started | Not Started | Not Started | Not Started |  | Ibtisam
Update Task | Not Started | Not Started | Not Started | Not Started |  | Ibtisam
My Notes
ViewMy Notes | Done | Done | Done | Done
View shared Notes | Done | In-progress | New Requerments | Waiting Pending Step |  | Gaith | فراز يحتاج يعدل api ، تم تعديلمن قبل فراز ولازم غيث يتاكد
Share Note | Done | In-progress | New Requerments | Waiting Pending Step |  | Gaith | فراز يحتاج يعدل api ، تم تعديلمن قبل فراز ولازم غيث يتاكد
Create new Note | Done | Done | Fix bug | Waiting Pending Step |  | Madawi | الهاشتاق مازالت فقط ٣ ومايحتاج نحدد عدد عليها ، description label issue
View Details | Done | Done | Done | Done
Note Action ( View, Delete, edit, pin) | Done | Done | Done | Done
Workspaces
Personal workspace | Done | Enhancement | Enhancement | Waiting Pending Step |  | Gaith
Main Workspace | Done | Enhancement | Enhancement | Waiting Pending Step |  | Gaith
Teams Workspace | Done | Enhancement | Enhancement | Waiting Pending Step |  | Gaith
Create Team Workspace | Done | Enhancement | Enhancement | Waiting Pending Step |  | Hossam
View overview (recent activities) | Done | Enhancement | Enhancement | Waiting Pending Step |  | Gaith
Posts (add post, react, comment, pin, delete, edit, update status) | Done | Enhancement | Enhancement | Waiting Pending Step |  | Gaith
Tasks (plannner)(Add plan, add task, delete, edit) | Done | In-progress | In-progress | Waiting Pending Step |  | Gaith
Goals (Add goal, delete, edit, update status) | Done | Enhancement | Enhancement | Waiting Pending Step |  | Gaith
upload file (upload, detete) | Done | In-progress | Waiting Pending Step | Waiting Pending Step |  | Gaith | get file id from existing upload file api reponse, then save worksapce id with file in databse, based on workpace id show files
Polls (create new, voting, cancel, view result) | Done | In-progress | In-progress | Waiting Pending Step |  | Salman
Notes (Add new, visibility, edit, delete, pin) | Done | Enhancement | Enhancement | Waiting Pending Step |  | Gaith
Members ( Add, update permissions, remove) | Done | Enhancement | Enhancement | Waiting Pending Step |  | Gaith
updates notification | Done | Done | Done | In-progress |  | Luma
Wihteboard
Create new (draw, write, note,etc) | Done | Enhancement | Waiting Pending Step | Waiting Pending Step |  | Salman
Live work | Done | Enhancement | Waiting Pending Step | Waiting Pending Step |  | Salman
delete | Done | Enhancement | Waiting Pending Step | Waiting Pending Step |  | Salman
update and auto save | Done | Enhancement | Waiting Pending Step | Waiting Pending Step |  | Salman
chat | Done | Enhancement | Waiting Pending Step | Waiting Pending Step |  | Salman
share | Done | Enhancement | Waiting Pending Step | Waiting Pending Step |  | Salman
Social Network
Timeline | Enhancement | Not Started | Not Started | Not Started |  | Ibtisam
Communities | Enhancement | Not Started | Not Started | Not Started |  | Ibtisam
Thnaks | Enhancement | Not Started | Not Started | Not Started |  | Ibtisam
Management Post | Enhancement | Not Started | Not Started | Not Started |  | Ibtisam
Profile | Enhancement | Not Started | Not Started | Not Started |  | Ibtisam
share post | Enhancement | Not Started | Not Started | Not Started |  | Ibtisam
Delete | Done | Not Started | Not Started | Not Started |  | Ibtisam
Reaction and comments | Done | Not Started | Not Started | Not Started |  | Ibtisam
apply Media Team Ruls and conditions | New Requerments | Not Started | Not Started | Not Started |  | Ibtisam
Global Search | Enhancement | Not Started | Not Started | Not Started |  | Ibtisam
Home page | Enhancement | New Requerments | New Requerments | New Requerments |  | Ibtisam
Side menu | Enhancement | New Requerments | New Requerments | New Requerments |  | Ibtisam
Navigation Dock | Enhancement | New Requerments | New Requerments | New Requerments |  | Ibtisam
AI chat (Gosi brain) | Done | Done | Done | Done
notification center
teams | Done | Fix bug | Waiting Pending Step | Waiting Pending Step |  | Gaith | تفاصيل تيمز
Filter | Done | Done | Done | Done
Dissapear completed notification | Done | Fix bug | Done | Waiting Pending Step |  | gaith | طلبات ساين
read/ unread | Done | Done | Done | Done
view all system integrated | Done | Fix bug | Done | Waiting Pending Step |  | gaith | teams
view all updates recent activity in workspace | Done | Not Started | Not Started | Not Started |  | Gaith | كمرحلة اولى ممكن نحدد اسم ورك سبيس واسم التاب كتنبية عام بوجود تحديث بعدها يصير دقيق ومحدد بالضبط يعني ادا تم اسناد هدف لموظف معين يصل التنبية للموظف المعني فقط
request date | Done | Fix bug | Done | Waiting Pending Step |  | Gaith | كل الطلبات لازم يكون وقت وصول الطلب في النظام الاساسي

## Sheet2
Done | Aiman
In-progress | Salman
Enhancement | Luma
Fix bug | Madawi
New Requerments | Gaith
Cancelled | Hossam
Waiting Pending Step | Ibtisam
Not Started
N/A